## Overview
uStock UAT Testing Tracker
Generated: 18 May 2026 ¦ Environment: https://ustock.unitymicrofund.com
TEAM & RESPONSIBILITIES
Person | Role | Modules Owned | Phases
Tester 1 | Test Lead | Auth · User Mgmt · Settings · Dashboard | P1, P7, P8 + Final Sign-off
Tester 2 | Sales Tester | Customers · Sales Orders · Delivery · Sales Returns · Sales Reports | P1, P3, P6
Tester 3 | Purchase Tester | Vendors · Purchase Orders · Goods Receives · Purchase Returns · Purchase Reports | P1, P4, P6
Tester 4 | Inventory Tester | Products · Warehouses · Transfers · Adjustments · Scrapping · Stock Count · Reports | P1, P2, P5, P6
TIMELINE (3 days)
Day | Morning | Afternoon
Day 1 | Phase 1 — Setup (all 4 testers together) | Phase 2 — Master Data + Phase 3 — Sales Flow (parallel)
Day 2 | Phase 4 — Purchase Flow + Phase 5 — Inventory (parallel) | Phase 6 — Reports + Phase 7 — Access Control
Day 3 | Bug fixes by dev + Retesting failed cases | Phase 8 — Settings + Final Sign-off
PHASE SUMMARY
Phase | Description | Owner | Tests | Status
P1 | Setup & Configuration | All Testers | 13 | Pending
P2 | Master Data (Products, Warehouses) | Tester 4 | 18 | Pending
P3 | Sales Flow SO → Delivery → Return | Tester 2 | 18 | Pending
P4 | Purchase Flow PO → GR → Return | Tester 3 | 18 | Pending
P5 | Inventory Movements | Tester 4 | 21 | Pending
P6 | Reports Verification | All Testers | 9 | Pending
P7 | Access Control & Role Testing | Tester 1 | 10 | Pending
P8 | Profile, Settings & Todos | Tester 1 | 11 | Pending
TOTAL |  |  | 118
SIGN-OFF CRITERIA
✓ Zero Critical bugs open
✓ Zero High bugs open (or accepted with documented workaround)
✓ Full cycle tested: PO → Goods Receive → SO → Delivery → Stock Report shows correct numbers
✓ All 4 testers sign off on their phase sheets
✓ Test Lead (Tester 1) gives final approval on Sign-Off sheet

## P1 - Setup
uStock UAT — Phase 1: Setup & Configuration [ Owner: All Testers ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Authentication | Admin login | Go to /Accounts/Login → enter admin@root.com / 123456 | Dashboard loads successfully |  | Not Tested
2 | User Mgmt | Create Tester 2 account | Admin → Users → New → enter Sales Tester email & password | User created, visible in user list |  | Not Tested
3 | User Mgmt | Create Tester 3 account | Admin → Users → New → enter Purchase Tester email & password | User created |  | Not Tested
4 | User Mgmt | Create Tester 4 account | Admin → Users → New → enter Inventory Tester email & password | User created |  | Not Tested
5 | Roles | Assign Sales roles → Tester 2 | Users → Tester 2 → assign: Customers, CustomerGroups, CustomerCategories, CustomerContacts, SalesOrders, SalesReports, SalesReturns, DeliveryOrders | Roles saved |  | Not Tested
6 | Roles | Assign Purchase roles → Tester 3 | Users → Tester 3 → assign: Vendors, VendorGroups, VendorCategories, VendorContacts, PurchaseOrders, PurchaseReports, PurchaseReturns, GoodsReceives | Roles saved |  | Not Tested
7 | Roles | Assign Inventory roles → Tester 4 | Users → Tester 4 → assign: Products, ProductGroups, Warehouses, UnitMeasures, TransferOuts, TransferIns, PositiveAdjustments, NegativeAdjustments, Scrappings, StockCounts, TransactionReports, StockReports, MovementReports | Roles saved |  | Not Tested
8 | Settings | Configure Company info | Settings → My Company → fill name, address, contact → Save | Company info saved |  | Not Tested
9 | Settings | Create Tax rate | Settings → Tax → New → Name: VAT, Rate: 10% → Save | Tax appears in order dropdowns |  | Not Tested
10 | Settings | Verify Number Sequences | Settings → Number Sequences → check SO and PO prefixes exist | Sequences present with correct format |  | Not Tested
11 | Login Test | Tester 2 login | Log in with Tester 2 credentials | Only Sales menu items visible |  | Not Tested
12 | Login Test | Tester 3 login | Log in with Tester 3 credentials | Only Purchase menu items visible |  | Not Tested
13 | Login Test | Tester 4 login | Log in with Tester 4 credentials | Only Inventory menu items visible |  | Not Tested

## P2 - Master Data
uStock UAT — Phase 2: Master Data [ Owner: Tester 4 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Unit Measures | Create 'Pieces' | Inventory → Unit Measures → New → Name: Pieces | Unit created |  | Not Tested
2 | Unit Measures | Create 'Kg' | Create unit Name: Kg | Unit created |  | Not Tested
3 | Unit Measures | Create 'Box' | Create unit Name: Box | Unit created |  | Not Tested
4 | Unit Measures | Edit unit measure | Edit 'Box' → change description → Save | Change saved |  | Not Tested
5 | Unit Measures | Delete unit measure | Delete 'Box' → confirm | Unit no longer in list (soft deleted) |  | Not Tested
6 | Product Groups | Create product group | Inventory → Product Groups → New → Name: TEST-Group-01 | Group created |  | Not Tested
7 | Product Groups | Edit product group | Edit TEST-Group-01 → rename → Save | Change saved |  | Not Tested
8 | Products | Create TEST-Product-01 | Inventory → Products → New → fill name, group, unit, price | Product created |  | Not Tested
9 | Products | Create TEST-Product-02 | Create second product | Product created |  | Not Tested
10 | Products | Create TEST-Product-03 | Create third product | Product created |  | Not Tested
11 | Products | Upload product image | Edit TEST-Product-01 → upload image → Save | Image visible on product record |  | Not Tested
12 | Products | Edit product price | Edit TEST-Product-01 → change price → Save | Price updated |  | Not Tested
13 | Products | Delete product | Create a temp product → delete it | Not in list, not in order dropdowns |  | Not Tested
14 | Warehouses | Create Main Warehouse | Inventory → Warehouses → New → Name: TEST-Main-Warehouse | Warehouse created |  | Not Tested
15 | Warehouses | Create Secondary Warehouse | New → Name: TEST-Secondary-Warehouse | Warehouse created |  | Not Tested
16 | Warehouses | Edit warehouse | Edit TEST-Main-Warehouse → update description → Save | Change saved |  | Not Tested
17 | Warehouses | Verify 6 system warehouses | Check list for: Customer, Vendor, Transfer, Adjustment, StockCount, Scrapping | All 6 present |  | Not Tested
18 | Warehouses | Try delete system warehouse | Attempt to delete 'Customer' system warehouse | Blocked — error message shown |  | Not Tested

## P3 - Sales Flow
uStock UAT — Phase 3: Sales Flow [ Owner: Tester 2 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Customer Mgmt | Create Customer Group | Sales → Customer Groups → New → TEST-CustGroup-01 | Group created |  | Not Tested
2 | Customer Mgmt | Create Customer Category | Sales → Customer Categories → New → TEST-CustCat-01 → link to group | Category created |  | Not Tested
3 | Customer Mgmt | Create Customer | Sales → Customers → New → TEST-Customer-01 → link group & category | Customer created |  | Not Tested
4 | Customer Mgmt | Create Customer Contact | Sales → Customer Contacts → New → link to TEST-Customer-01 | Contact created |  | Not Tested
5 | Customer Mgmt | Edit Customer | Edit TEST-Customer-01 → change address → Save | Change saved |  | Not Tested
6 | Sales Orders | Create Sales Order | Sales → Sales Orders → New → select TEST-Customer-01 → add 2 products with qty → apply VAT tax | SO created with auto-number SO-XXXX |  | Not Tested
7 | Sales Orders | Verify SO status = Draft | Check Status field on new SO | Status = Draft |  | Not Tested
8 | Sales Orders | Confirm Sales Order | Click Confirm on the SO | Status changes from Draft |  | Not Tested
9 | Sales Orders | Generate SO PDF | Click PDF button → download | PDF downloads with correct data |  | Not Tested
10 | Delivery Orders | Create Delivery Order | Inventory → Delivery Orders → New → link to confirmed SO → set qty | DO created |  | Not Tested
11 | Delivery Orders | Confirm Delivery Order | Confirm the DO | DO status = Confirmed |  | Not Tested
12 | Stock Check | Verify stock DOWN after DO | Inventory → Stock Report → filter TEST-Main-Warehouse → TEST-Product-01 | Stock decreased by delivered qty |  | Not Tested
13 | Sales Returns | Create Sales Return | Inventory → Sales Returns → New → link to DO | Return created |  | Not Tested
14 | Sales Returns | Confirm Sales Return | Confirm the return | Return confirmed |  | Not Tested
15 | Stock Check | Verify stock UP after return | Check Stock Report again | Stock back to pre-delivery level |  | Not Tested
16 | Sales Reports | Verify SO in Sales Report | Sales → Sales Reports → filter by date range covering test SO | SO appears with correct amounts & tax |  | Not Tested
17 | Edge Case | Deliver more than ordered | Create DO with qty > SO qty | System blocks or shows warning |  | Not Tested
18 | Edge Case | Delete confirmed SO | Try to delete a confirmed Sales Order | Error shown, delete prevented |  | Not Tested

## P4 - Purchase Flow
uStock UAT — Phase 4: Purchase Flow [ Owner: Tester 3 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Vendor Mgmt | Create Vendor Group | Purchase → Vendor Groups → New → TEST-VendGroup-01 | Group created |  | Not Tested
2 | Vendor Mgmt | Create Vendor Category | Purchase → Vendor Categories → New → TEST-VendCat-01 | Category created |  | Not Tested
3 | Vendor Mgmt | Create Vendor | Purchase → Vendors → New → TEST-Vendor-01 → link group & category | Vendor created |  | Not Tested
4 | Vendor Mgmt | Create Vendor Contact | Purchase → Vendor Contacts → New → link to TEST-Vendor-01 | Contact created |  | Not Tested
5 | Vendor Mgmt | Edit Vendor | Edit TEST-Vendor-01 → change details → Save | Change saved |  | Not Tested
6 | Purchase Orders | Create Purchase Order | Purchase → Purchase Orders → New → select TEST-Vendor-01 → add 2 products → apply VAT | PO created with auto-number PO-XXXX |  | Not Tested
7 | Purchase Orders | Verify PO status = Draft | Check Status field on new PO | Status = Draft |  | Not Tested
8 | Purchase Orders | Confirm Purchase Order | Click Confirm | Status changes |  | Not Tested
9 | Purchase Orders | Generate PO PDF | Click PDF → download | PDF downloads correctly |  | Not Tested
10 | Goods Receives | Create Goods Receive | Inventory → Goods Receives → New → link to confirmed PO → set qty | GR created |  | Not Tested
11 | Goods Receives | Confirm Goods Receive | Confirm the GR | GR confirmed |  | Not Tested
12 | Stock Check | Verify stock UP after GR | Inventory → Stock Report → TEST-Main-Warehouse → TEST-Product-01 | Stock increased by received qty |  | Not Tested
13 | Purchase Returns | Create Purchase Return | Purchase → Purchase Returns → New → link to GR | Return created |  | Not Tested
14 | Purchase Returns | Confirm Purchase Return | Confirm the return | Return confirmed |  | Not Tested
15 | Stock Check | Verify stock DOWN after return | Check Stock Report | Stock decreased back |  | Not Tested
16 | Purchase Reports | Verify PO in Purchase Report | Purchase → Purchase Reports → filter by date | PO appears with correct amounts |  | Not Tested
17 | Edge Case | Receive more than ordered | Create GR with qty > PO qty | System blocks or warns |  | Not Tested
18 | Edge Case | Delete confirmed PO | Try to delete confirmed PO | Error shown, delete prevented |  | Not Tested

## P5 - Inventory
uStock UAT — Phase 5: Inventory Movements [ Owner: Tester 4 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Transfer Out | Create Transfer Out | Inventory → Transfer Out → New → From: TEST-Main → Product: TEST-Product-01 → Qty: 5 | Transfer Out created |  | Not Tested
2 | Transfer Out | Confirm Transfer Out | Confirm the Transfer Out | Status = Confirmed |  | Not Tested
3 | Stock Check | Stock DOWN in source warehouse | Stock Report → TEST-Main-Warehouse → TEST-Product-01 | Stock decreased by 5 |  | Not Tested
4 | Transfer In | Create Transfer In | Inventory → Transfer In → New → To: TEST-Secondary → link to Transfer Out | Transfer In created |  | Not Tested
5 | Transfer In | Confirm Transfer In | Confirm the Transfer In | Status = Confirmed |  | Not Tested
6 | Stock Check | Stock UP in dest warehouse | Stock Report → TEST-Secondary-Warehouse → TEST-Product-01 | Stock increased by 5 |  | Not Tested
7 | Transaction Rpt | Verify both transfers appear | Transaction Report → filter by product | Transfer Out and Transfer In both listed |  | Not Tested
8 | Pos Adjustment | Create Positive Adjustment | Inventory → Positive Adjustments → New → TEST-Product-01 → Qty: 10 → TEST-Main | Adjustment created |  | Not Tested
9 | Pos Adjustment | Confirm Positive Adjustment | Confirm | Confirmed |  | Not Tested
10 | Stock Check | Stock UP by 10 | Stock Report | Stock +10 |  | Not Tested
11 | Neg Adjustment | Create Negative Adjustment | Inventory → Negative Adjustments → New → TEST-Product-01 → Qty: 5 | Adjustment created |  | Not Tested
12 | Neg Adjustment | Confirm Negative Adjustment | Confirm | Confirmed |  | Not Tested
13 | Stock Check | Stock DOWN by 5 | Stock Report | Stock -5 |  | Not Tested
14 | Edge Case | Negative adj > available stock | Create Negative Adjustment for qty > current stock | System warns or blocks |  | Not Tested
15 | Scrapping | Create Scrapping | Inventory → Scrapping → New → TEST-Product-02 → Qty: 2 | Scrapping created |  | Not Tested
16 | Scrapping | Confirm Scrapping | Confirm | Confirmed |  | Not Tested
17 | Stock Check | Stock DOWN after scrapping | Stock Report → TEST-Product-02 | Stock -2 |  | Not Tested
18 | Stock Count | Create Stock Count | Inventory → Stock Count → New → Warehouse: TEST-Main | Stock Count created |  | Not Tested
19 | Stock Count | Enter counted quantities | Enter qty: match system for P-01, differ for P-02 | Quantities entered |  | Not Tested
20 | Stock Count | Confirm Stock Count | Confirm | Adjustments recorded for differences |  | Not Tested
21 | Stock Check | Stock Report matches count | Stock Report → TEST-Main-Warehouse | Quantities equal the counted values |  | Not Tested

## P6 - Reports
uStock UAT — Phase 6: Reports Verification [ Owner: All Testers ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Sales Report | All SOs appear in report | Sales → Sales Reports → date range covering test period | All test SOs listed |  | Not Tested
2 | Sales Report | SO amounts correct | Cross-check total amounts vs what was entered in SO | Amounts match |  | Not Tested
3 | Purchase Report | All POs appear in report | Purchase → Purchase Reports → date range covering test period | All test POs listed |  | Not Tested
4 | Purchase Report | PO amounts correct | Cross-check totals vs PO data | Amounts match |  | Not Tested
5 | Stock Report | Final stock per warehouse | Inventory → Stock Report → filter TEST warehouses | Stock levels correct after all transactions |  | Not Tested
6 | Stock Report | Manual cross-check | Sum all In movements - Out movements per product manually → compare to report | Report matches manual calculation |  | Not Tested
7 | Transaction Rpt | All movements listed | Transaction Report → full date range | Every delivery, receipt, transfer, adjustment, scrapping present |  | Not Tested
8 | Transaction Rpt | In/Out types correct | Check each row has correct type (In or Out) | Types are correct |  | Not Tested
9 | Movement Report | Product movement summary | Inventory → Movement Reports → view per product | Correct total In, total Out, net per product |  | Not Tested

## P7 - Access Control
uStock UAT — Phase 7: Access Control [ Owner: Tester 1 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | Role Filter | Create single-role user | Admin → Users → New → assign ONLY 'SalesOrders' role | User created |  | Not Tested
2 | Role Filter | Login as single-role user | Login with single-role user account | Menu shows ONLY Sales Orders item |  | Not Tested
3 | Role Filter | Other menus hidden | Verify Products, Warehouses etc. not in menu | Hidden items not visible |  | Not Tested
4 | Unauth Access | Direct URL blocked | Manually type /Products/ProductList in browser while logged as single-role user | Access blocked — error or redirect to login |  | Not Tested
5 | No Role | Create zero-role user | Create user → assign NO roles → Save | User created |  | Not Tested
6 | No Role | Login as zero-role user | Login with no-role account | Empty menu — no pages accessible |  | Not Tested
7 | Role Update | Add role to user | Admin → Users → add 'Products' role to single-role user | Role saved |  | Not Tested
8 | Role Update | Verify new menu after re-login | Log out and in again as that user | Products now visible in menu |  | Not Tested
9 | Role Update | Remove role | Admin → Users → remove 'Products' role | Role removed |  | Not Tested
10 | Role Update | Menu updated after re-login | Log out and in again | Products no longer in menu |  | Not Tested

## P8 - Settings
uStock UAT — Phase 8: Profile & Settings [ Owner: Tester 1 ]
STATUS LEGEND → | Not Tested | Pass | Fail | Blocked | N/A
# | Category | Test Case | Steps to Reproduce | Expected Result | Actual Result | Status | Notes
1 | My Profile | Update name | Profiles → My Profile → change First/Last name → Save | Name updated in header |  | Not Tested
2 | My Profile | Upload avatar | My Profile → upload picture → Save | Avatar shows in top-right header |  | Not Tested
3 | My Profile | Change password | My Profile → Change Password → enter current + new password → Save | Password changed |  | Not Tested
4 | My Profile | Login with new password | Logout → login with new password | Login successful |  | Not Tested
5 | Company | Update company info | Settings → My Company → update name, address, logo → Save | Changes saved |  | Not Tested
6 | Company | Company shown on PDF | Generate any SO or PO PDF | Company name/address in PDF header |  | Not Tested
7 | Num Sequences | Edit SO prefix | Settings → Number Sequences → edit Sales Order prefix to 'TST-SO' | Prefix updated |  | Not Tested
8 | Num Sequences | New SO uses updated prefix | Create a new Sales Order | SO number uses 'TST-SO' prefix |  | Not Tested
9 | Todos | Create Todo | Utilities → Todo → New → Title: Test Todo | Todo created, visible in list |  | Not Tested
10 | Todo Items | Create Todo Item | Utilities → Todo Items → New → link to Test Todo | Item created |  | Not Tested
11 | Todos | Delete Todo | Delete Test Todo → confirm | Todo removed from list |  | Not Tested

## Bug Tracker
uStock UAT — Bug Tracker
SEVERITY → | Critical | High | Medium | Low
# | Date | Tester | Module | Page / URL | Steps to Reproduce | Expected | Actual | Severity | Assigned To | Status | Fixed In | Verified By | Notes

## Requirements Log
uStock UAT — New Requirements Log
# | Date | Requested By | Module | Description | Priority | Effort Estimate | Decision | Target Release | Status | Notes

## Sign-Off
uStock UAT — Final Sign-Off Sheet
Phase | Description | Owner | Total | Passed | Failed | Blocked | Sign-Off Date | Approved | Comments
P1 | Setup & Configuration | All Testers | 13 |  |  |  |  | Pending
P2 | Master Data | Tester 4 | 18 |  |  |  |  | Pending
P3 | Sales Flow | Tester 2 | 18 |  |  |  |  | Pending
P4 | Purchase Flow | Tester 3 | 18 |  |  |  |  | Pending
P5 | Inventory Movements | Tester 4 | 21 |  |  |  |  | Pending
P6 | Reports Verification | All Testers | 9 |  |  |  |  | Pending
P7 | Access Control | Tester 1 | 10 |  |  |  |  | Pending
P8 | Profile & Settings | Tester 1 | 11 |  |  |  |  | Pending
FINAL | Overall UAT Sign-Off | Tester 1 (Test Lead) | ALL |  |  |  |  | Pending